## Alert Ticket
S.No | TICKET_ID | Description | Priority | Dev Name | Status | Comments | QA Verified Date | Type | Work Hours
1 | ALRT-1022 | Update Callout CTA for all Gap emails | Normal | Gowtham | QA Verified |  | 2017-11-02 | Story
2 | ALRT-1016 | Banana Republic - Update image with CTA | Critical | Gowtham | QA Verified | Back to development/Nikita raised seperate ticket for bug ALRT-1028 and closed it | 2017-01-11 | CR
3 | ALRT-1026 | Update fonts for Athleta email templates | Normal | Gowtham | QA Verified |  | 2017-11-03 | CR
4 | ALRT-1029 | Amway URLS | Normal | Gowtham | QA Verified |  | 2017-11-06 | Task
5 | ALRT-1046 | Make Hero Images clickable | Critical | Gowtham | QA Verified |  | 2017-11-07 | CR
6 | ALRT-1043 | Gap - Update hero image in alert emails | Normal | Vinoth E | QA Verified |  | 2017-11-07 | CR
7 | ALRT-1042 | Banana Republic - Email compatibility issues | Critical | Vinoth E | QA Verified |  | 2017-11-08 | CR
8 | ALRT-1045 | Old Navy Alerts - Design Feedback - Round 3 | Critical | Gowtham | QA Verified | Sam Peters find merchant image issue in Delivery attempt | 2017-11-09 | CR
9 | ALRT-969 | Banana Republic - Update Header font for all alerts to title case and futura bold | Blocker | Gowtham | QA Verified |  | 2017-11-08 | CR
10 | ALRT-1047 | Gap - Update Care link to include category id | Critical | Gowtham | QA Verified |  | 2017-11-08 | Task
11 | ALRT-967 | Banana Republic - Update Top Nav | Critical | Gowtham | QA Verified |  | 2017-11-08 | CR
12 | ALRT-1050 | Edit HTML email for Ralph Lauren alerts - Change header and Fonts | Major | Gowtham | QA Verified | Back to development | 2017-11-09 | Task
13 | ALRT-1048 | Athleta alerts - Nav menu update | Major | Vinoth E | QA Verified |  | 2017-11-10 | CR
14 | ALRT-1061 | Modification to Delayed Email Alert for Gamestop | Normal | Vinoth E | QA Verified |  | 2017-11-10 | CR
15 | ALRT-1062 | Update hero images for Gap Alerts - All 3 use cases | Critical | Gowtham | QA Verified |  | 2017-11-10 | Task
16 | ALRT-1063 | Replace marketing assets - Gap Alerts | Critical | Vinoth E | QA Verified |  | 2017-11-13 | Task
17 | ALRT-870 | Build HTML email for Academy alerts - Ship Confirmation | Major | Vinoth E | QA Verified |  | 2017-11-14 | Task
18 | ALRT-871 | Edit HTML email for Academy Alerts | Major | Vinoth E | QA Verified |  | 2017-11-14 | Task
1 | ALRT-1095 | Update subject line for Gap Alert emails - all use cases | Critical | Vinoth M | QA Verified | Subject validation done only in master branch through jenkins job. QA verify will do once code merged | 2017-11-20 | CR
2 | ALRT-1080 | Delay Email - Creative Feedback | Major | Vinoth E | QA Verified |  | 2017-11-20 | CR
3 | ALRT-1081 | Delivered Email - Creative Feedback | Major | Vinoth E | QA Verified |  | 2017-11-20 | CR
4 | ALRT-1082 | Delivery Attempt Email- Creative Feedback | Major | Vinoth E | QA Verified |  | 2017-11-20 | CR
5 | ALRT-1144 | Gamestop Delayed Alert Modification | Nomal | Vinoth E | QA Verified |  | 2017-11-27 | CR
6 | ALRT-1142 | edit punctuation for Gap alert subject lines | Nomal | Vinoth E | QA Verified |  | 2017-11-30 | CR
7 | ALRT-1140 | Brownells Alerts Link Update | Nomal | Vinoth E | QA Verified |  | 2017-11-30 | CR
8 | ALRT-1155 | Increase Image size - Delivered, Delayed, Delivery Attempt Email | Nomal | Vinoth E | QA Verified |  | 2017-12-01 | CR
9 | ALRT-1183 | Delayed, Delivered, Delivery Attempt Email - Increase image size for "Products that have arrived" | Major | Vinoth E | QA Verified |  | 2017-12-12 | CR
10 | ALRT-1173 | Correct text on the Delivery Attempt email alert | Minor | Vinoth E | QA Verified |  | 2017-12-12 | CR
| ALRT-1177 | Ralph Lauren: Fix Salutation in body text | Nomal | Vinoth E | QA Verified |  | 2017-12-12 | CR
| ALRT-1187 | 4. Build HTML email for JCPenney alerts (Delivery) | Major | Vinoth E | QA Verified |  | 2017-12-13 | CR
| ALRT-1230 | 4. Build HTML email for Buy Buy Baby US alerts | Major | Vinoth E | QA Verified |  | 2017-12-20 | CR
| ALRT-1238 | 4. Build HTML email for Buy Buy Baby CA alerts | Major | Vinoth E | QA Verified |  | 2017-12-20 | CR
| ALRT-1197 | 4. Build HTML email for Chico's alerts | Blocker | Vinoth E | QA Verified |  | 2017-12-29 | CR
| ALRT-1249 | Build HTML email for TOMS alerts | Major | Vinoth E | QA Verified |  | 2018-01-02 | CR
| ALRT-1258 | Build Shipment Confirmation HTML email for Finishline alerts | Major | Vinoth E | QA Verified |  | 2018-01-03 | CR
| ALRT-1276 | Redirect urls for Chanel View Order Details Button | Normal | Vinoth E | QA Verified |  | 2018-01-04 | Task
| ALRT-1268 | 4. Edit HTML email for JCPenney alerts (Delivery) v1 | Major | Vinoth E | QA Verified |  | 2018-01-10 | CR
| ALRT-1273 | Edit HTML email for Academy Alerts - v2 | Major | Vinoth E | QA Verified |  | 2018-01-11 | CR
| ALRT-1288 | Final Version of Redirect urls for Chanel | Normal | Vinoth E | QA Verified |  | 2018-01-10 | Task
| ALRT-1287 | rei - Delivered Build Email | Normal | Vinoth E | QA Verified |  | 2018-01-10 | CR
| ALRT-1301 | rei - Delayed - Build Email | Normal | Vinoth E | QA Verified |  | 2018-01-10 | CR
| ALRT-1313 | REI - Delivery_Attempt - Build Email | Normal | Vinoth E | QA Verified |  | 2018-01-10 | CR
| ALRT-1348 | 4. Edit HTML email for JCPenney alerts (Delivery) v2 | Major | Vinoth E | QA Verified |  | 2018-01-16 | CR
| ALRT-1205 | Build HTML email for WHBM alerts | Major | Vinoth E | QA Verified |  | 2018-01-16 | CR
| ALRT-1340 | Update Care Links in Gap Templates | Normal | Vinoth E | QA Verified |  | 2018-01-17 | Task
| ALRT-1315 | Edit HTML email for Chicos | Major | Vinoth E | QA Verified |  | 2018-01-17 | CR
| ALRT-1342 | Edit HTML email for Academy Alerts - v3 | Major | Vinoth E | QA Verified |  | 2018-01-19 | CR
| ALRT-1289 | eddiebauer - Delivered Build Email | Normal | Vinoth E | QA Verified |  | 2018-01-31 | CR
| ALRT-1296 | eddiebauer - Delayed Build Email | Normal | Vinoth E | QA Verified |  | 2018-01-31 | CR
| ALRT-1319 | Update URLs with UTM code for Athleta Alert emails | Normal | Vinoth E | QA Verified |  | 2018-01-18 | CR
| ALRT-1357 | Add UTM tags to Gap Alert emails | Normal | Vinoth E | QA Verified |  | 2018-01-19 | CR
| ALRT-1293 | 4. Build HTML email for Puritan's Pride alerts | Major | Vinoth E | QA Verified |  | 2018-01-19 | CR
| ALRT-1354 | 4. Edit HTML email for JCPenney alerts (Delivery) v3 | Major | Vinoth E | QA Verified |  | 2018-02-08 | CR
| ALRT-1341 | DSW - Update Alerts Templates with link to CARE in Footer | Normal | Vinoth E | QA Verified |  | 2018-01-23 | CR
| ALRT-1164 | DSW - Please Create Return Initiation Alert Template | Normal | Vinoth E | QA Verified |  | 2018-01-23 | CR
| ALRT-1384 | Change Chanel CTA Button Wording and Color | Normal | Vinoth E | QA Verified |  | 2018-01-29 | Task
| ALRT-1383 | Edit HTML for Chanel Alerts - change headline font and from html to image | Normal | Vinoth E | QA Verified |  | 2018-01-29 | Task
| ALRT-1381 | 4. Edit HTML email for BBB alerts (Delayed) v1 | Major | Vinoth E | QA Verified |  | 2018-01-30 | CR
| ALRT-1385 | Ralph Lauren - Display Shipping Address in Email Body | Normal | Vinoth E | QA Verified |  | 2018-01-30 | CR
| ALRT-975 | 4. Build Delivery Attempt, Delayed HTML email for JCPenney alerts | Major | Vinoth E | QA Verified |  | 2018-01-30 | CR
| ALRT-1314 | Athleta - Move Navigation bar to the bottom of alerts emails for mobile and deskto | Normal | Vinoth E | QA Verified |  | 2018-01-30 | Task
| ALRT-1300 | eddiebauer - Delivery Attempt Build Email | Normal | Vinoth E | QA Verified |  | 2018-01-31 | CR
| ALRT-1387 | Edit HTML email for Soma - v2 | Normal | Vinoth E | QA Verified |  | 2018-01-31 | CR
| ALRT-1388 | Edit HTML email for WHBM - v2 | Normal | Vinoth E | QA Verified |  | 2018-01-31 | CR
| ALRT-1386 | Edit HTML email for Chicos - v2 | Normal | Vinoth E | QA Verified |  | 2018-01-31 | CR
| ALRT-1389 | Edit HTML email for Chico's Off The Rack - v2 | Normal | Vinoth E | QA Verified |  | 2018-01-31 | CR
| ALRT-1353 | JCPenney: Show or Hide Item View based on Order Data | Major | Vinoth E | QA Verified |  | 2018-02-01 | CR
| ALRT-1321 | 4. Build HTML email for Chico's Off The Rack alerts | Major | Vinoth E | QA Verified |  | 2018-02-01 | Task
| ALRT-1316 | 4. Build HTML email for Soma alerts | Major | Vinoth E | QA Verified |  | 2018-02-01 | CR
| ALRT-1382 | Edit Logo in HTML e-mails for Mobile and Desktop Alerts | Normal | Vinoth E | QA Verified |  | 2018-02-02 | Task
| ALRT-1220 | 4. Build HTML email for Bed Bath Beyond CA alerts | Major | Vinoth E | QA Verified |  | 2018-02-02 | CR
| ALRT-1364 | Move Marketing Assets in Alert Emails Below Tracking Information + Add Phone Number Below "More Questions" | Normal | Vinoth E | QA Verified |  | 2018-02-05 | Task
| ALRT-1374 | 4. Build HTML email for Catbird alerts | Major | Vinoth E | QA Verified |  | 2018-02-07 | Task
| ALRT-615 | Build HTML email for Lenovo | Major | Vinoth E | QA Verified |  | 2018-02-07 | Task
| ALRT-1417 | 4. Edit HTML email for JCPenney alerts v4 | Major | Vinoth E | QA Verified |  | 2018-02-08 | CR
| ALRT-1409 | Build Delivery Anticipation HTML email for Finishline alerts | Major | Vinoth E | QA Verified |  | 2018-02-12 | CR
| ALRT-1336 | Build HTML Email for GS Love Alerts | Normal | Vinoth E | QA Verified |  | 2018-02-15 | Task | 1
| ALIMP-28 | Academy Sports - Image URL | Major | Vinoth E | QA Verified |  | 2018-02-15 | Story | 2
| ALIMP-4 | Remove link to CARE in Gap Alerts | Normal | Vinoth E | QA Verified |  | 2018-02-15 | Task | 2
| ALIMP-58 | 4. Edit HTML email for JCPenney alerts v7 (All Templates) | Major | Vinoth E | QA Verified |  | 2018-02-15 | CR | 1
| ALIMP-55 | 4. Edit HTML email for JCPenney alerts v6 (Delayed Delivery) | Major | Vinoth E | QA Verified |  | 2018-02-15 | CR | 2
| ALIMP-54 | 4. Edit HTML email for JCPenney alerts v5 (Attempted Delivery) | Major | Vinoth E | QA Verified |  | 2018-02-15 | CR | 2
| ALIMP-68 | Brownells: Update Asset in Alerts Emails | Normal | Vinoth E | QA Verified |  | 2018-02-22 | CR
| ALIMP-69 | Edit HTML email for Buy Buy Baby US alerts- V1 | Major | Vinoth E | QA Verified |  | 2018-02-22 | CR
| ALIMP-70 | Edit HTML email for Bed Bath Beyond CA Alerts- V1 | Major | Vinoth E | QA Verified |  | 2018-02-22 | CR

## Return Ticket
S.No | TICKET_ID | Description | Priority | Dev Name | Status | Comments | QA Verified Date | Type
1 | RTN-5769 | Orvis - Build Default Returns Page | Normal | Gautham/Sriram | Closed | Actual Implementation moved | 2018-01-03 | CR
2 | RTN-5444 | Chicos Off The Rack - Build Default Returns Page | Major | Gautham/Sriram | QA Verified | Actual Implementation moved | 2018-01-03 | CR
3 | RTN-5165 | The Bay (Hudsons Bay) - Build Default Returns Page | Major | Gautham/Sriram | QA Verified |  | 2018-01-03 | CR
4 | RTN-4237 | Worx (Positec) Brands- Build Default Returns Page | Normal | Gautham/Sriram | QA Verified |  | 2018-01-05 | CR
5 | RTN-4242 | Rockwell Tools (Positec) Brands- Build Default Returns Page | Normal | Gautham/Sriram | QA Verified |  | 2018-01-05 | CR
6 | RTN-5143 | Disney - Build Default Returns Page | Normal |  |  | Branch return reason confirmation waiting |  | CR
7 | RTN-5147 | Saks Fifth Avenue - Build Default Returns Page | Normal |  |  | Retailer data mismatch |  | CR
8 | RTN-5169 | Off 5th - Build Default Returns Page | Normal |  |  | Retailer data mismatch |  | CR
9 | RTN-5173 | Lord and Taylor - Build Default Returns Page | Normal | Gautham/Sriram | QA Verified | Retailer data mismatch/updated in QA | 2018-02-02 | CR
10 | RTIMP-664 | Saks Fifth Avenue - Build Default Returns Page | Normal | Gautham/Sriram | QA Verified |  | 2018-01-24 | CR
11 | RTIMP-506 | Sally Beauty - Build Default Returns Page | Normal | Gautham/Sriram | QA Verified |  | 2018-01-25 | CR
12 | RTIMP-667 | Off 5th - Build Default Returns Page | Normal | Gautham/Sriram | QA Verified |  | 2018-01-29 | CR
| RTIMP-1011 | Marine Layer - Build Default Returns Page | Normal | Gautham/Sriram | QA Verified |  | 2018-02-06 | CR
| RTIMP-606 | Ralph Lauren - Build Default Returns Page | Normal | Gautham/Sriram | QA Verified |  | 2018-02-13 | CR
| RTIMP-601 | Lily Pulitzer - Build Default Returns Page | Normal | Gautham/Sriram | QA Verified |  | 2018-02-16 | CR

## Return Bug Ticket
6092 | BUG_ID | Description | Priority | Logged Date | Dev Name | Status | Comments | QA Verified Date
1 | RTN-4579 | Rebecca Minkoff :: Return confirmation logo mismatch | Normal |  | SK | QA Verified |  | 2017-11-01
| RTN-5411 | ILoveDooney1 :: Link underlined color different in Firefox & IE | Normal | 2017-11-23 | Gautham | QA Verified |  | 2017-11-27
| RTN-5412 | ILoveDooney1 :: Text scattered in Internet Explorer Browser | Major | 2017-11-23 | Gautham | QA Verified |  | 2017-11-27
| RTN-5413 | Saks Fifth Avenue :: Give vertical space between menu border and menus | Normal | 2017-11-24 | Gautham | QA Verified |  | 2017-11-27
| RTN-5414 | Saks Fifth Avenue :: Menu background color mismatch in Mobile | Normal | 2017-11-24 | Gautham | QA Verified |  | 2017-11-27
| RTN-5425 | ShopDisney :: TELL US ABOUT YOUR RETURN label not visible in step2 | Normal | 2017-11-27 | Gautham | QA Verified |  | 2017-11-30
| RTN-5426 | ShopDisney :: Menu space issue | Normal | 2017-11-27 | Gautham | QA Verified |  | 2017-11-30
| RTN-5427 | ShopDisney :: Link underlined color different in Firefox & IE | Normal | 2017-11-27 | Gautham | QA Verified |  | 2017-12-01
| RTN-5428 | ILoveDooney1 :: Menu character space issue in IE | Normal | 2017-11-27 | Gautham | QA Verified |  | 2017-12-05
| RTN-5429 | ShopDisney :: Mobile view issue | Normal | 2017-11-27 | Gautham | QA Verified |  | 2017-11-30
| RTN-5469 | ShopDisney :: Return confirmation mail logo shrinked | Normal | 2017-11-30 | Gautham | QA Verified |  | 2017-12-05
| RTN-5470 | ShopDisney :: Menu font are bold in Firefox and Safari | Normal | 2017-11-30 | Gautham | QA Verified |  | 2017-12-04
| RTN-5537 | Saks Fifth Avenue: Return confirmation mail logo shrinked | Normal | 2017-12-06 | Gautham | QA Verified |  | 2017-12-13
| RTN-5641 | Saks Fifth Avenue: "TELL US ABOUT YOUR RETURN" header is invisible | Normal | 2017-12-13 | Gautham | QA Review | Jason working for data mismatch
| RTN-5842 | Rockwell Tools (Positec) :: Carriers not displaying in Step2 | Major | 2017-12-21 | SriRam | QA Verified |  | 2017-12-26
| RTN-5863 | ShopDisney ::Logo panel border missing in Mobile view | Major | 2017-12-22 | Gautham | QA Verified |  | 2018-01-05
| RTN-5864 | ShopDisney ::Menu panel border shade missing | Normal | 2017-12-22 | Gautham | QA Verified |  | 2017-12-29
| RTN-5865 | The Bay (Hudsons Bay) :: Carriers not displaying in Step2 | Major | 2017-12-22 | SriRam | QA Verified |  | 2017-12-26
| RTN-5866 | The Bay (Hudsons Bay) :: URL underlined with black instead blue in Firefox | Normal | 2017-12-26 | Gautham | QA Verified |  | 2018-01-03
| RTN-5867 | Rockwell Tools (Positec) :: URL underlined with black instead green in Firefox | Normal | 2017-12-26 | Gautham | QA Verified |  | 2018-01-03
| RTN-5868 | Rockwell Tools (Positec) :: Header panel too long | Normal | 2017-12-26 | Gautham | QA Verified |  | 2018-01-03
| RTN-5879 | Orvis :: Carriers not displaying in Step2 | Major | 2017-12-27 | SriRam | Closed | Actual Implementation moved | 2018-01-03
| RTN-5893 | Chicos Off The Rack :: Return confirmation mail logo shrinks | Normal | 2017-12-28 | Gautham | QA Review | Actual Implementation moved
| RTN-5894 | Chicos Off The Rack :: Mobile View : Menu Background colour & logo size mismatch | Normal | 2017-12-28 | Gautham | QA Review | Actual Implementation moved
| RTN-5907 | Worx (Positec) Brands :: URL underlined with black instead orange in Firefox | Normal | 2018-01-02 | Gautham | QA Verified |  | 2018-01-05
| RTN-5918 | Rockwell Tools (Positec) :: Header panel split into two lines in Firefox | Normal | 2018-01-03 | Gautham | QA Verified |  | 2018-01-05
| RTIMP-646 | Saks Fifth Avenue: "TELL US ABOUT YOUR RETURN" header is invisible | Major | 2017-12-12 | Gautham | QA Verified | Actual Implementation moved | 2018-01-24
| RTIMP-1008 | Off 5th : TELL US ABOUT YOUR RETURN not visible | Normal | 2018-01-24 | Gautham | QA Verified |  | 2018-01-29
| RTIMP-1009 | Off 5th : Return confirmation mail logo override | Normal | 2018-01-24 | SriRam | QA Verified |  | 2018-01-25
| RTIMP-1030 | Sally Beauty :: Navigation menu mouse over issue | Normal | 2018-01-25 | Gautham | QA Verified |  | 2018-01-29
| RTIMP-1031 | Sally Beauty :: Menu font different in IE browser | Normal | 2018-01-25 | Gautham | QA Verified |  | 2018-01-29
| RTIMP-1055 | Sally Beauty : Step2 "Find a UPS drop-off location" link underlined with black in Firefox & IE | Normal | 2018-01-29 | Gautham | QA Verified |  | 2018-01-30
| RTN-6092 | Lord and Taylor :: Step2 "Find a UPS drop-off location" link underlined with black in Firefox & IE | Normal | 2018-02-01 | Gautham | QA Verified |  | 2018-02-02
| RTN-6093 | Lord and Taylor :: Decrease space between navigation menu in mobile client | Normal | 2018-02-01 | Gautham | QA Verified |  | 2018-02-02
| RTIMP-1213 | Marine Layer :: Return confirmation mail log shrinked | Minor | 2018-02-07 | Gautham | QA Verified |  | 2018-02-09
| RTIMP-1224 | Lily Pulitzer :: Navigation menu issue | Normal | 2018-02-09 | Gautham | QA Verified |  | 2018-02-14
| RTIMP-1225 | Lily Pulitzer :: Return confirmation mail logo not displayed | Normal | 2018-02-09 | Gautham | QA Verified |  | 2018-02-14
| RTIMP-1226 | Lily Pulitzer :: Shipping label issue | Normal | 2018-02-09 | SriRam | QA Verified |  | 2018-02-15
| RTIMP-1227 | Lily Pulitzer :: "Find a UPS drop-off location" link underline colour issue in firefox and IE | Normal | 2018-02-09 | Gautham | QA Verified |  | 2018-02-16
| RTIMP-1228 | Ralph Lauren :: Return page - Mobile issues | Normal | 2018-02-09 | Gautham | QA Verified |  | 2018-02-13
| RTIMP-1229 | Ralph Lauren :: "TELL US ABOUT YOUR RETURN" header is invisible | Normal | 2018-02-09 | Gautham | QA Verified |  | 2018-02-13
| RTIMP-1230 | Ralph Lauren:: Return confirmation mail logo not displayed | Normal | 2018-02-09 | Gautham | QA Verified |  | 2018-02-13
| RTIMP-1231 | Ralph Lauren :: "Find a UPS drop-off location" link underline colour issue in firefox and IE | Normal | 2018-02-09 | Gautham | QA Verified |  | 2018-02-13

## TRACK
TICKET_ID | Description | Priority | Dev Name | Status | Comments | QA Verified Date | Type | Created Date
CAR-121 | Academy Sports - Ceva Carrier : Wrong carrier tracking url mapped in Narvar tracking page | Normal | Karthick | QA Verified |  | 2017-12-26 | Bug
CAR-5 | Update Ontrac Flat File mappings | Normal | Karthick | QA Verified | Reassign to dev | 2017-11-13 | Task
CAR-3 | Implement UK Mail | Task | Karthick | QA Verified | Tracking page not reflecting from DB | 2017-12-28 | Blocker
TRK-6069 | Sonos: dhlexpresseu not displaying tracking info for numbers beginning with "JV" | Blocker | Karthick | QA Verified |  | 2017-11-17 | Improvement
TRK-6025 | Add Carriers to Carrier_Info Table | Normal | Karthick | QA Verified |  | 2017-11-17 | Task
TRK-6007 | Vitacup Carrier Integration with Newgistics | Blocker | Karthick | QA Verified |  | 2017-11-17 | CR
CAR-91 | Collect Plus - PLT | Normal | Karthick | QA Verified |  | 2017-11-30 | Task
CAR-107 | New Carrier Integration: Truckmaster | Normal | Karthick | QA Verified |  | 2017-12-29 | Epic
CAR-131 | New Carrier Integration: Truckmaster - Carrier URL | Normal | Jason Huber | Backlog |  |  | Bug | 2017-12-29
CAR-95 | New Carrier Integration: New England Motor Freight | Normal | Karthick | QA Verified |  | 2017-12-29 | CR
TRK-5413 | Add CarrierStatusCode Mapping Cache to carrier_info evictors | Normal | Sriram | QA Verified |  | 2018-01-02 | Improvement
CAR-94 | New Carrier Integration: USF Holland | Normal | Karthick | QA Verified |  | 2018-01-03 | CR
CAR-97 | New Carrier Integration: USF Reddaway | Normal | Karthick | QA Verified | Mapping not given for some status | 2018-01-04 | CR
CAR-132 | Schneider - failure to process all scans in EDI fil | Normal | Karthick | QA Verified |  | 2018-01-09 | Bug
CAR-133 | USPack - Showing In Transit when Delivered | Normal | Karthick | QA Verified |  | 2018-01-09 | Bug
CAR-84 | Need a direct carrier integration with Estafeta | Normal | Karthick | QA Verified |  | 2018-01-09 | Epic
CAR-142 | Estafeta - Mistakenly mapped with aftership | Blocker | Karthick | QA Verified |  | 2018-01-09 | Bug
CAR-143 | Estafeta - Tracking status code mapping required | Normal | Jason Huber | QA Verified |  | 2018-01-10 | Bug | 2018-01-09
TRK-6386 | OnePeleton/Dispatch track - Finished status record not handled with M/D/YY date format | Normal | Sriram | QA Verified |  | 2018-01-17 | Bug | 2018-01-17
TRK-6373 | Estimated Delivery Date - Code Changes required | Critical | Sriram | QA Verified |  | 2018-01-17 | Bug
TRK-6343 | Returns Tracking: Newgistics Tracking # Hyperlinks to BirchBox page | Normal | Karthick | QA Verified |  | 2018-01-18 | Bug
CAR-178 | Home Depot - SAIA hyperlink | Normal | Karthick | QA Verified |  | 2018-01-23 | Story
TRK-5710 | Birchbox - set up BestWay integration to begin digesting EDD from flat file | Major | Karthick |  | Reported the bug on 14Nov17 |  | CR
CAR-179 | Home Depot - Estes Express hyperlink | Normal | Karthick | QA Verified |  | 2018-01-23 | CR
CAR-174 | Home Depot - USF Holland hyperlink | Normal | Karthick | QA Verified |  | 2018-01-23 | CR
CAR-165 | Fastmile - Showing In Transit when Delivered | Normal | Karthick | QA Verified |  | 2018-01-29 | Bug
CAR-166 | JW Logistics - Showing In Transit when Delivered | Normal | Karthick | QA Verified |  | 2018-01-29 | Bug
CAR-133 | USPack - Showing In Transit when Delivered | Normal | Karthick | QA Verified |  | 2018-01-29 | Bug
CAR-182 | Fastmile - AG event comes after any event not updates Guarantee delivery date | Major | Karthick | QA Verified |  | 2018-01-25 | Bug | 2018-01-24
CAR-183 | USPack - AG event comes after any event not updates Guarantee delivery date | Major | Karthick | QA Verified |  | 2018-01-25 | Bug | 2018-01-24
CAR-184 | JW Logistics - AG event comes after any event not updates Guarantee delivery date | Major | Karthick | QA Verified |  | 2018-01-25 | Bug | 2018-01-24
CAR-185 | Fastmile/Uspack/Jw logistics - AG(EDD) event process issue | Major | Karthick | QA Verified |  | 2018-01-29 | Bug | 2018-01-25
CAR-181 | New Carrier Integration: New Penn | Major | Karthick | QA Verified |  | 2018-01-29 | CR
CAR-175 | Home Depot - USF Reddaway hyperlink | Normal | Karthick | QA Verified |  | 2018-01-30 | CR
CAR-205
CAR-206
CAR-200
CAR-203
CAR-204
CAR-186 | Tractor Supply - update carrier moniker from truckmaster to VENL | Normal | Sriram | QA Verified |  | 2018-02-06 | Task
CAR-210 | Event Description Needs to be Updated for JDSports/Blacks DPDU | Normal | Karthick | QA Verified |  | 2018-02-06 | Bug
CAR-192 | DHL Carrier URL is malformed | Normal | Sriram | QA Verified |  | 2018-02-07 | Bug
CAR-188 | New Carrier Integration: Pitt Ohio | Normal | Karthick | QA Verified |  | 2018-02-12 | CR
CAR-154 | Asda - Implement UK Mail | Normal | Karthick | QA Verified |  | 2018-02-13 | CR
CAR-231 | Create redis cache key ukmail:authenticationTokenKe | Normal | Karthick | QA Verified |  | 2018-02-15 | Task
CAR-216 | Blacks/JD Sports -Update Royal Mail Mappings on UI | Major | Sriram | QA Verified |  | 2018-02-21 | bug
CAR-237 | Home Depot- YRC Carrier not working | Block | Karthick | QA Verified |  | 2018-02-21 | bug
CAR-232 | Ingest UK Mail updates from JDSports Metapack fil | Major | Sriram | QA Verified |  | 2018-02-21 | CR
CAR-242 | Point USF Holland and USF Reddaway to public API endpoint | Blocker | Karthick | QA Verified |  | 2018-02-22 | Task

## Alert Bug
S No | BUG_ID | Description | Priority | Logged Date | Dev Name | Status | Comments | QA Verified Date | Work Hours
1 | ALRT-993 | Athleta: Marketing image URL's incorrect | Major | 2017-10-27 | Vinoth Elumalai | QA Verified |  | 30/10/2017
1 | ALRT-994 | Athleta: Mobile Client issues | Major | 2017-10-27 | Vinoth Elumalai | QA Verified |  | 30/10/2017
1 | ALRT-1009 | Academy :: All Email : Product name not bold for IOS client | Major | 2017-10-27 | Vinoth Elumalai | QA Verified |  | 31/10/2017
2 | ALRT-1010 | Academy :: All Email : Gmail in Internet Explorer browser - Item image are in big size | Minor | 2017-10-27 | Vinoth Elumalai | QA Verified | Invalid Ticket | 2017-11-01
3 | ALRT-1011 | Academy :: Delivery email - SEE FULL ORDER DETAILS link mismatch | Major | 2017-10-27 | Vinoth Elumalai | QA Verified |  | 2017-11-03
4 | ALRT-994 | Athleta: Mobile Client issues | Major |  | Vinoth Elumalai | QA Verified | Shilpi created and I verified | 30/10/2017
5 | ALRT-960 | Gap - Remove Disclaimer | Normal |  | Gowtham | QA Verified |  | 2017-10-31
6 | ALRT-999 | Athleta: Nav item issues | Major |  | C | QA Verified |  | 2017-10-31
7 | ALRT-1014 | Athleta - Menu items are not aligned in all email clients | Normal |  | Gowtham | QA Verified |  | 2017-10-31
8 | ALRT-1012 | Increase spacing between Item name & item attributes in outlook | Normal |  | Gowtham | QA Verified |  | 2017-10-31
9 | ALRT-1017 | Amway :: Product name not wrap in Package details for outlook client | Normal | 2017-10-31 | Gowtham | QA Verified |  | 2017-11-01
10 | ALRT-1023 | Academy :: Street name in Uppercase for Delivered ma | Normal | 2017-11-01 | Gowtham | QA Verified |  | 2017-11-01
11 | ALRT-1024 | Academy :: Correct the spelling of Outdoors in all emails | Major | 2017-11-01 | Gowtham | QA Verified |  | 2017-11-01
12 | ALRT-951 | BR - URL is displayed on the template in outlook firefox | Normal |  | Vinoth Elumalai | QA Verified |  | 2017-11-01
13 | ALRT-556 | Theory: Multishipment section error | Major |  | Gowtham | QA Verified |  | 2017-11-01
14 | ALRT-992 | Theory Bug | Major |  | Gowtham | QA Verified | Back to development and fixed | 2017-11-06
15 | ALRT-1028 | Marketing Image not rendered in outlook | Nomal |  | Gowtham | QA Verified |  | 2017-11-02
16 | ALRT-1002 | BR: Bugs | Major |  | Gowtham | QA Verified |  | 2017-11-02
17 | ALRT-1001 | BR: Mobile Client issues | Major |  | Gowtham | QA Verified |  | 2017-11-03
18 | ALRT-958 | Athleta Menu item - text folding | Normal |  | Gowtham | QA Verified |  | 2017-11-03
19 | ALRT-1035 | Academy :: Delayed Email - Change the second CTA - Primary CTA Design | Major | 2017-11-03 | Gowtham | QA Verified |  | 2017-11-06
20 | ALRT-1041 | Academy :: Shipment Confirmation - Primay CTA text change | Normal | 2017-11-06 | Vinoth Elumalai | QA Verified |  | 2017-11-09
21 | ALRT-894 | Ralph: retailer callout text is incorrect | Major |  | Vinoth Elumalai | QA Verified |  | 2017-11-08
22 | ALRT-953 | Blurry logo & text in mobile clients | Normal |  | Gowtham | QA Verified |  | 2017-11-08
23 | ALRT-1055 | Old Navy :: Image render issue in outlook | Nomal | 2017-11-08 | Gowtham | QA Verified |  | 2017-11-09
24 | ALRT-1056 | Ralph Lauren : MENU boarder not present in Outlook client | Normal | 2017-11-08 | Gowtham | QA Verified |  | 2017-11-10
25 | ALRT-1060 | Ralph Lauren : Correct spelling of Ralph Lauren in message tex | Major | 2017-11-09 | Gowtham | QA Verified | Back to development/10-11 | 2017-11-10
26 | ALRT-1058 | Delivered Email- See Full Order Details button links to the wrong url | Major |  | Gowtham | QA Verified |  | 2017-11-09
27 | ALRT-1064 | Ralph Lauren : Logo expand in some client | Major | 2017-11-10 | Gowtham | QA Verified |  | 2017-11-10
28 | ALRT-1071 | Gamestop :: Image Render issue outlook client | Normal | 2017-11-10 | Vinoth Elumalai | QA Verified |  | 2017-11-13
29 | ALRT-1072 | GameStop : Outlook client issue - TRACK THIS PACKAGE button not left align | Normal | 2017-11-13 | Vinoth Elumalai | QA Verified |  | 2018-02-02
30 | ALRT-1092 | Academy :: Shipment confirmation mail - Invalid subject | Normal | 2017-11-15 | Vinoth M | QA Verified | Subject validation done only in master branch through jenkins job. QA verify will do once code merged | 2017-11-20
31 | ALRT-1093 | Ralph Lauren :: Add space between tracking number and CTA button | Normal | 2017-11-15 | Vinoth Elumalai | QA Verified |  | 2017-11-15
32 | ALRT-1094 | Ralph Lauren :: Gmail Mobile client - Menu in two lines | Major | 2017-11-15 | Vinoth Elumalai | QA Verified |  | 2017-11-15
33 | ALRT-1091 | Ralph lauren logo is too big in apple mail | Normal |  | Vinoth Elumalai | QA Verified |  | 2017-11-15
34 | ALRT-1090 | Alignment of marketing assets in all the templates | Normal |  | Vinoth Elumalai | QA Verified |  | 2017-11-16
35 | ALRT-1097 | Ralph Lauren : More Questions not linking to RL FAQ page | Normal |  | Vinoth Elumalai | QA Verified |  | 2017-11-16
36 | ALRT-1098 | Ralph Lauren : "Sale" nav li not linking to correct page | Normal |  | Vinoth Elumalai | QA Verified |  | 2017-11-16
37 | ALRT-1096 | Ralph Lauren : See Full Order Details button not linking to RL Accounts page | Normal |  | Vinoth Elumalai | QA Verified |  | 2017-11-17
38 | ALRT-1114 | Ralph Lauren : Update UTM Tags in Emails | Normal |  | Vinoth Elumalai | QA Verified |  | 2017-11-17
39 | ALRT-1113 | Ralph Lauren : Remove "GIFTS" and add "CUSTOMIZE" to email header | Normal |  | Vinoth Elumalai | QA Verified |  | 2017-11-20
40 | ALRT-1128 | Theory :: Add space between tracking number and CTA button in outlook client | Normal | 2017-11-20 | Vinoth Elumalai | QA Verified |  | 2017-11-20
41 | ALRT-1139 | Ralph Lauren :: Delivery Anticipation - Outlook 2016 CTA Border issue | Normal | 2017-11-21 | Vinoth Elumalai | Closed | Directly closed
42 | ALRT-1145 | See full order details should point to accounts page | Normal |  | Vinoth Elumalai | QA Verified |  | 2017-11-28
43 | ALRT-1146 | Gamestop :: Add space between tracking number and CTA button | Normal | 28/11/2017 | Vinoth Elumalai | QA Verified |  | 2017-11-30
44 | ALRT-1153 | Gamestop :: Add space between tracking number and CTA button - all templates | Normal |  | Vinoth Elumalai | QA Verified |  | 2017-12-01
45 | ALRT-1222 | JCPenney :: Logo header text wrapped | Normal | 2017-12-13 | Vinoth Elumalai | QA Verified |  | 2017-12-13
46 | ALRT-1223 | JCPenney :: Gmail in Internet Explorer - Image size | Normal | 2017-12-13 | Vinoth Elumalai | QA Verified |  | 2017-12-13
47 | ALRT-1224 | JCPenney :: More Questions wrong link | Normal | 2017-12-13 | Vinoth Elumalai | QA Verified |  | 2017-12-13
| ALRT-1245 | See full order details should redirect to a correct url | Normal |  | Vinoth Elumalai | QA Verified |  | 2017-12-14
| ALRT-1261 | Buy Buy Baby - Message salutation, text & callout not left aligned | Normal |  | Vinoth Elumalai | QA Verified |  | 2017-12-20
| ALRT-1263 | Chicos :: Add space between tracking number and CTA button | Normal | 2017-12-26 | Vinoth Elumalai | QA Verified |  | 2017-12-26
| ALRT-1265 | Chicos :: Accessories menu wrap in Ipad clien | Major | 2017-12-26 | Vinoth Elumalai | QA Verified |  | 2017-12-26
| ALRT-1264 | Chicos :: Sales menu differes color from track page | Normal | 2017-12-26 | Vinoth Elumalai | QA Verified |  | 2017-12-26
| ALRT-1267 | Chicos :: UTM_Campaign tag change into URL of CTA button | Normal | 2017-12-26 | Vinoth Elumalai | QA Verified |  | 2017-12-26
| ALRT-1266 | Chicos :: Menus wrap in Yahoo client | Normal | 2017-12-26 | Vinoth Elumalai | QA Verified |  | 2017-12-26
| ALRT-1269 | Toms :: Delayed,Delivered Mail - Header menu issue | Major | 2017-12-28 | Vinoth Elumalai | QA Verified |  | 2018-01-02
| ALRT-1270 | TOMS :: Add link to logo | Major | 2017-12-28 | Vinoth Elumalai | QA Verified |  | 2017-12-29
| ALRT-1274 | Toms : Delivered - SEE FULL ORDER DETAILS - Change URL | Normal | 2018-01-02 | Vinoth Elumalai | QA Verified |  | 2018-01-02
| ALRT-1272 | Redirect urls for Chanel | Normal |  | Vinoth Elumalai | QA Verified |  | 2018-01-03
| ALRT-1280 | JCPenney alerts (Delivery) :: Increase vertical space of attributes in Undelivered shipment section | Normal | 2018-01-04 | Vinoth Elumalai | QA Verified |  | 2018-01-04
| ALRT-1277 | Toms - Increase the spacing between the item attributes | Normal |  | Vinoth Elumalai | QA Verified |  | 2018-01-04
| ALRT-1279 | Chanel templates not displaying the correct image size | Normal |  | Vinoth Elumalai | QA Verified |  | 2018-01-05
| ALRT-1281 | JCPenny - See Full order details invalid url | Normal | 2018-01-04 | Vinoth Elumalai | QA Verified |  | 2018-01-05
| ALRT-1328 | Academy Alerts - v2 :: Package detail section images are small size in Outlook client | Normal | 2018-01-10 | Vinoth Elumalai | QA Verified |  | 2018-01-11
| ALRT-1329 | Academy Alerts - v2 :: Order no bar overlapped with Menu label b | Normal | 2018-01-10 | Vinoth Elumalai | QA Verified |  | 2018-01-10
| ALRT-1330 | Academy Alerts - v2 :: Images are over size in Gmail (Explorer) | Normal | 2018-01-10 | Vinoth Elumalai | QA Verified |  | 2018-01-11
| ALRT-1286 | Chanel templates missing or not displaying the correct image size for all images in some emails | Normal |  | Vinoth Elumalai | QA Verified |  | 2018-01-10
| ALRT-1285 | Chanel templates not displaying the correct image size for Sunglasses | Normal |  | Vinoth Elumalai | QA Verified |  | 2018-01-10
ALRT-1338
| ALRT-1343 | Rei Template : Outlook issue | Major | 2018-01-12 | Vinoth Elumalai | QA Verified |  | 2018-01-12
| ALRT-1344 | Rei Template : Header font size small in mobile client | Normal | 2018-01-12 | Vinoth Elumalai | QA Verified |  | 2018-01-12
| ALRT-1345 | Rei Template : Unshipment items image size is huge in Gmail(Interner Explorer) clien | Normal | 2018-01-12 | Vinoth Elumalai | QA Verified |  | 2018-01-12
| ALRT-1346 | Rei Template : Shop Rei link top align in Yahoo mail client | Normal | 2018-01-12 | Vinoth Elumalai | QA Verified |  | 2018-01-12
| ALRT-1347 | Rei Template : Order detail font is small in mobile client
| ALRT-1355 | Eddie Bauer :: Bold and increase the size of menu | Normal | 2018-01-17 | Vinoth Elumalai | QA Verified |  | 2018-01-17
| ALRT-1312 | retailer-image-grid should stack the images in mobile | Normal |  | Vinoth Elumalai | QA Verified |  | 2018-01-17
| ALRT-1349 | Academy templates subject has ascii characters | Normal |  | Vinoth Elumalai | QA Verified |  | 2018-01-17
| ALRT-1350 | Academy - EDD in ship confirmation template | Normal |  | Vinoth Elumalai | QA Verified |  | 2018-01-19
| ALRT-1351 | Academy - Outlook spacing for order number & item attr | Normal |  | Vinoth Elumalai | QA Verified |  | 2018-01-19
| ALRT-1361 | Puritans Pride :: Move the logo to left side | Major | 2018-01-19 | Vinoth Elumalai | QA Verified |  | 2018-01-19
| ALRT-1362 | Puritans Pride :: See Full Order Details CTA button wrapped in Gmail App (iOS 10.3.2) | Normal | 2018-01-19 | Vinoth Elumalai | QA Verified |  | 2018-01-19
| ALRT-1366 | Jcpenny :: Subject are mismatched in delivered template | Major | 2018-01-22 | Vinoth Elumalai | QA Verified |  | 2018-01-22
| ALRT-1367 | Puritan's Pride :: Product not aligned properly | Major | 2018-01-22 | Vinoth Elumalai
| ALRT-1378 | DSW - Return Initiation Template: Change the font of Address | Normal | 2018-01-23 | Vinoth Elumalai | QA Verified |  | 2018-01-23
| ALRT-1379 | DSW - Return Initiation Template : Adjust the menu space in Mobile client | Normal | 2018-01-23 | Vinoth Elumalai | QA Verified |  | 2018-01-23
| ALRT-1380 | DSW - Return Initiation Template : Left align the header | Normal | 2018-01-23 | Vinoth Elumalai | QA Verified |  | 2018-01-23
| ALRT-1393 | BBB(Delayed) :: Attribute space not even in delayed template | Major | 2018-01-30 | Vinoth Elumalai | QA Verified |  | 2018-01-30
| ALRT-1394 | BBB(Delayed) :: Product image size are bigger in Internet Explorer client | Normal | 2018-01-30 | Vinoth Elumalai | QA Verified |  | 2018-01-30
| ALRT-1395 | BBB(Delayed): CTA button not aligned in outlook | Normal | 2018-01-30 | Vinoth Elumalai | QA Verified |  | 2018-01-30
| ALRT-1400 | Soma : Menu Misaligned and wrapped in outlook 2016 | Normal | 2018-01-31 | Vinoth Elumalai | QA Verified |  | 2018-02-01
| ALRT-1401 | Chico's Off The Rack :: Muti-shipment section arriving date not displayed | Major | 2018-01-31 | Vinoth Elumalai | QA Verified |  | 2018-02-01
| ALRT-1402 | Chico's Off The Rack : Current shipment section arriving date not display in Iphone and Ipad client | Major | 2018-01-31 | Vinoth Elumalai | QA Verified |  | 2018-02-01
| ALRT-1399 | Athleta - Attribute space issue in current and unshipped item | Normal | 2018-01-31 | Vinoth Elumalai | QA Verified |  | 2018-02-02
| ALRT-1404 | Catbird :: Change subject of delayed template | Normal | 2018-02-02 | Vinoth Elumalai | QA Verified |  | 2018-02-07
| ALRT-1405 | Catbird :: Remove line space between salutation and message text in delivery anticipation | Normal | 2018-02-02 | Vinoth Elumalai | QA Verified |  | 2018-02-07
| ALRT-1406 | Catbird :: Add utm tag to marketing image lin | Normal | 2018-02-02 | Vinoth Elumalai | QA Verified |  | 2018-02-07
| ALRT-1407 | Lenovo :: Increase attribute space in Unshipped section | Normal | 2018-02-02 | Vinoth Elumalai | QA Verified |  | 2018-02-07
| ALRT-1408 | Lenovo : Change the url for "SEE FULL ORDER DETAILS" CTA button | Normal | 2018-02-02 | Vinoth Elumalai | QA Verified |  | 2018-02-07
| ALRT-1415 | Brownells - Shipment confirmation :: Issues | Normal | 2018-02-06 | Gautham | QA Verified |  | 2018-02-06
| ALRT-651 | Brownells - Shipment confirmation email edits | Normal |  | Vinoth Elumalai | QA Verified |  | 2018-02-06
| ALRT-1416 | Catbird :: "SEE FULL ORDER DETAILS" CTA button text wrapped in Delivered Template | Normal | 2018-02-07 | Vinoth Elumalai | QA Verified |  | 2018-02-07
| ALRT-1424 | GS Love :: Template order change | Normal | 2018-02-12 | Vinoth Elumalai | QA Verified |  | 2018-02-15